## Sheet1
sprint backlog | story point | sprint task | assign role | estimated effort | day 1 | day2 | day 3 | day 4 | day 5 | day 6
Sprint 1: Schedule of program | 13 | Analyse the requirements for showing the program schedule | Analyst | 8 | 4 | 2 | 3 | 0 | 1 | 2 | 12
|  | Designing of the schedule of program page | Designer | 12 | 2 | 3 | 1 | 4 | 3 | 1 | 14
|  | Creating the database for schedule of program page | Database Designer | 7 | 2 | 1 | 3 | 1 | 1 | 1 | 9
|  | Implement database list into program schedule. | Developer | 15 | 2 | 4 | 1 | 4 | 2 | 0 | 13
|  | do testing on the database to show the program schedule. | Tester | 8 | 1 | 1 | 2 | 1 | 0 | 0 | 5
Sprint 2: Latest News | 21 | analyse the user stories | Analyst | 7 | 1 | 2 | 1 | 2 | 2 | 2 | 10
|  | designing of the latest news page | Designer | 6 | 1 | 2 | 1 | 3 | 2 | 2 | 11
|  | Create latest news page | Developer | 15 | 2 | 3 | 2 | 2 | 3 | 3 | 15
|  | do test on the website visibility | Tester | 4 | 1 | 2 | 1 | 2 | 0 | 0 | 6
Sprint 3: Weather forecast | 8 | design the weather page | Designer | 5 | 1 | 0 | 0 | 1 | 1 | 0 | 3
|  | implement code to display the weather. | Developer | 8 | 2 | 3 | 1 | 2 | 2 | 1 | 11
|  | do testing to see if the weather forecast is visible. | Tester | 6 | 1 | 0 | 1 | 2 | 2 | 2 | 8
Sprint 4: About the Newspaper | 2 | Designing of the About Us page. | Designer | 8 | 1 | 3 | 1 | 2 | 0 | 0 | 7
|  | Develop the About Us page. | Developer | 10 | 3 | 2 | 2 | 1 | 2 | 1 | 11
|  | Testing on About Us page | Tester | 4 | 0 | 0 | 0 | 2 | 2 | 0 | 4
Sprint 5: Complain & Enqueries | 5 | Analyse on how to manage the queries | Analyst | 10 | 2 | 1 | 2 | 3 | 1 | 0 | 9
Sprint 6: Contact Details | 3 | Design the Contact us page | Designer | 12 | 3 | 2 | 2 | 1 | 2 | 2 | 12
|  | develop the contact us form | Developer | 15 | 3 | 3 | 2 | 1 | 3 | 3 | 15
|  | TOTAL ESTIMATED TIME |  | 160 | day 5: TOTAL ACTUAL TIME | 175